ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	3

2.1.	Overall objective	3

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	5

4.3.	Project management	5

5.	LOGISTICS AND TIMING	6

5.1.	Location	6

5.2.	Start date & period of implementation of tasks	6

6.	REQUIREMENTS	6

6.1.	Staff	6

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	7

8.1.	Definition of indicators	7

8.2.	Special requirements	7

# BACKGROUND INFORMATION

## Partner country

Republic of Albania

## Contracting authority

“Together For Life” organisation for Sustainable Development

## Country background

“Support Participation, Accountability and Civil Organisation Empowerment (SPACE)” project in Albania, was launched on 9 January 2023 and has a duration of 36 months, until January 2026. With the financed support of the European Union (EU).

The action focused and assessed public participation in preparation, implementation and monitoring of legislative drafts, government strategies and budgeting aiming (policy cycle) to increase transparency and accountability in the public sector strengthening CSOs capacities, especially local grassroots CSOs from different regions in Albania.

The project is implemented by the Together for Life (TFL) organisation as coordinator partner and BIRN Albania, Qëndresa Qytetare and Destiny Center for Excellence as implementing partners.

## Current situation in the sector

The action will target two crucial sectors:

Health and Education, as two sectors that has been highlighted by international community, but also action’ consortium CSOs as very problematic sectors.

Regarding health sector Albania is ranked 110th from Transparency International for its Corruption Perceptions Index, scoring 35 out 100 points during 2021. It also showed that 25% of the public service users paid a bribe in the previous 12 months. The TI reports showed that in Albania the pandemic was also used as an excuse to reduce oversight and accountability for public procurement and foreign aid spending, allowing corruption to spread widely.

Regarding education sector, the data shows that public universities during the academic year 2020 - 2021 spent only 0.4% of their budget on research and incurred high costs for furniture, fuel and building security, without publishing the values and details of their contracts. What's even more concerning is that, as a result of the Covid-19 outbreak, the aforementioned academic year was conducted entirely online, and neither free internet access, nor reduced tuition fees were offered to help students. Their empty buildings have been guarded with staggering figures over a calendar year. The University of Tirana spent 555,250 Euros for guards and 236,200 Euros for security cameras. In addition to these expenditures, 332,000 Euros were spent on heating.

## Related programmes and other donor activities

NA

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overarching objective of SPACE is to strengthen the engagement of CSOs in public policy processes/cycle through evidence-based advocacy and monitoring of reforms.

## Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

- Outcome 1: Civil society organizations will work better to demand improved accountability and budget transparency of public institutions (health and education sectors)

- Outcome 2. Increased public pressure on authorities to respond, change behaviour and reduce corruption.

- Outcome 3: CSOs, media, youth, state/non-state stakeholders work together to improve the budget transparency and accountability, leading to the better quality of services for the Albanian citizens.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Output 1.1: Provide a clear view on the needs and challenges faced by the grass-root CSOs on local level

Output 1.2: CSOs are enabled to monitor and advocate toward increased accountability and transparency of public institutions

Output 2.1: Local CSOs are supported with expertise and financial opportunities to increase pressure on public authorities to reduce corruption

Output 2.2: Media and local CSOs pressure public authorities to respond, change behaviour and reduce corruption

Output 3.1: CSOs, media and youth work together to identify the problems and solutions toward improved quality of service for the citizens

Output 3.2: Young people are engaged to improve the capacities of their peers as responsible citizens

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

All above-mentioned will (impact) contribute to the enhancement of democratic and accountability in central and local level in Albania.

The main assumptions are:

- General public attention is not diverted due to political agenda (elections: local and general, etc.) or Covid 19 Emergency situation.

- Enough CSOs and local government staff are willing to participate in interventions of the Action.

- There will be good information interchange and cooperation between civil society, project staff and the experts involved in the technical support activities.

- The project will have enough time and availability of resources for the fulfilment of all the tasks.

- Civil society organizations will be thirsty for knowledge and improvement.

- The public institutions are willing to be more transparent and accountable and more open toward civil society, seeing it as a partner and supporter.

- Targeted audience (academics, students, professionals, civil society, local residents) is responsive to the messages spread by the project.

## Risks

Key risks facing the project implementation include:

The main risk is the apathy of local grassroots CSOs and local media toward change. For this reason, the consortium has decided to focus especially on previous cooperation with several local CSOs that have really seen the success achieved after evidence-based advocacy. This is the main reason that the project will start with building capacities, where all the CSOs will have the possibility to be informed about the successful steps for successful advocacy and share best practices.

The political neutrality of the action will be provided by the steering committee which will be in charge for a careful plan that the SPACE project will not be misused. The successful previous experience and cooperation of “Together for Life” and BIRN Albania will be an important stepping stone for this risk given that local elections (2023) will take place at the start of the project implementation and general elections (2025) on the last year (project implementation is foreseen for 36 months: 2023-2025). While Qendresa Qytetare and DCE will ensure previous cooperation with youth target group to mitigate the potential risks.

The lack of will of public officials to cooperate and participate in this project is one of the risks, while the consortium will use previous contacts to explain the importance of this intervention and its objectives.

# SCOPE OF THE WORK

## General

### Description of the assignment

In the frame of this Action “Together for Life” will contract a monitoring and evaluation expert for the six organizations that have been awarded grants during the first phase of the sub-granting scheme.

### Geographical area to be covered

Project targeted geographical areas will be all regions of Albania.

### Target groups

The main target groups of the SPACE Project are:

- Local Grassroots CSOs – The project main target group are the local grassroots CSOs from different regions of the country. In a pre-evaluation phase, the consortium had meetings with several of these CSOs and identified some of their needs related to their watchdogging role, participation and contribution in decision-making processes, as well as in advocacy and raising awareness.

- Media and journalists – Are an important part of the action as they serve as a link between the community and all other societal actors, including civil society and state/non-state institutions. In the local level, the media and journalists need to better understand their role as watchdogs of the public institutions, identified as a need by the journalists themselves but even during the work in the field, especially from BIRN Albania with its network all over the country.

- Local and central government (health and education institutions) – public institutions are a target group of the action as well as beneficiaries. The action will involve the representatives of public institutions in the meetings with community, civil society and media, aiming to increase their links and their attitude (change behaviour).

- Youth are target groups and beneficiaries of this action. Albania is considered one of the countries with a young population, whose average age is 37.6 years (INSTAT, 2021). Changes and dynamics of current development require the energy and will of young people to engage in achievement SDG goals and in this case in education and health sectors. Their engagement in the action, constitute a milestone to improve a governance system in Albania.

## Specific work

- The expert will perform specific tasks under the general assignment on monitoring and evaluating the six organizations that have been awarded grants during the first phase of the sub-granting scheme. The specific works for this assignment are:

- Develop a M&E plan for each organization that has been awarded a grant during the first phase of the SPACE sub-granting scheme

- Collection of data from sub-grantees to assess their project progress, against agreed indicators and outcomes.

- Organize at least one field trip to each sub-grantee organization

- Periodically monitoring of sub-grantee organizations to ensure they are progressing according to their activity plan.

- Providing technical assistance to sub-grantee organizations in M&E data collection and reporting to improve their proficiency in completing effectively these tasks.

- Reviewing interim reports submitted by sub-grantees to ensure alignment with grant requirements.

- Support the sub-grantees to implement time management strategies to mitigate delays and ensure timely delivery of project activities.

### Responsible body

Together For Life

### Management structure

Decision-making process is regulated by Contracting Authority

### Facilities to be provided by the contracting authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

The Expert/Company will be in Tirana and serve in the SPACE project, covering all areas in Albania.

## Start date & period of implementation of tasks

The intended start date is July 2024 and the period of implementation of the contract will be 6 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Qualifications and skills

- Bachelor’s and master’s degree (or equivalent) in related fields

- Very good skills in writing and speaking English.

- Be able to communicate clearly and effectively.

- Strong time-management and organizational skills.

- To be able to ensure confidentiality of project information.

General professional experience

- Similar work experience with EU funded projects

The expert must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

N/A

# REPORTS

## Reporting requirements

The contractor will submit a report in English in one original copy:

Draft copy report of maximum 10 pages (main text, excluding annexes) for each subgrantee organization. The reports shall be submitted no later than 1week before the end of the period of implementation of tasks.

Final copy of the reports with the same specifications as the draft copies, incorporating any comments received from the parties on the draft report. The deadline for sending the final reports is 5 days after receipt of comments on the draft study. The reports shall contain a sufficiently detailed description of all the tasks conducted by the contractor during the implementation of the contract.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The following indicators will be used for monitoring and evaluation of the provided services:

- Timely implementation of the Project’s components and submission of deliverables in compliance with the Terms of Reference.

- Duties of the Consultant performed in compliance with the Conditions and all relevant paperwork completed.

- Works completed and handed over within the established deadlines.

- Timely submission and approval of all reports.

- Availability of the Consultant as indicated in the tender proposal and concluded in the Contract.

- High quality of all Contract outputs, approval of the documents by the Project Manager, Contracting Authority and other relevant local authorities.

## Special requirements

NA