# TERMS OF REFERENCE

# Expert/ researcher for conducting an assessment of public perception of corruption in the healthcare sector

Name of the Project:      “Citizens for Transparency: Tackling Corruption in Albanian Healthcare sector”

Reference number:          EuropeAid/174080/DD/ACT/

# Job title:                           Expert/ researcher for conducting an assessment of public perception of

# corruption in the healthcare sector.

# Location:                          Albania

Duration:                         29 January 2025 – 14 April 2025

# BACKGROUND INFORMATION

# 1.1 Contracting authority

"Together for Life" (TFL) association is a non-political, non-governmental and not-for-profit organization, established in late 2009 as an initiative of a group of reputable journalists as a membership organization. TFL has undertaken a range of innovative and successful projects and activities.

It has gained reputation as the first and most prominent organization dealing in health rights in the country; as well as has expanded its activity to promote the debate on the building of civil society and a culture of good governance and human rights in Albania; with a focus on vulnerable communities; communities living in remote or economically less advantaged areas; women and youth. It was founded on values of transparency, participatory approach; teamwork; commitment and efficiency based on the principles of development and coordination of all stakeholders in the development process.

# 1.2 Background of the Project

Together for Life is implementing the project “Citizens for Transparency: Tackling Corruption in Albanian Healthcare sector” part of the subgrating scheme of the project “Civil Society against corruption – from a local challenge to a European Response”, implemented by Albanian Helsinki Committee (AHC), in partnership with: Albanian Legal and Territorial Research Institute (ALTRI Centre) & Friends of Europe (FoE), with funding from the European Commission.

The project aims to address the pervasive issue of corruption in the Albanian healthcare sector, ranked as one of the most corrupted sectors in the country. The consequences of this corruption on people’s lives are immense. Empirical evidence shows that corruption reduces immunization rates, delays the vaccination of newborns, discourages the use of public healthcare centres, reduces public resources available for medical equipment, drugs, and salaries; distorts health policies; denies citizens access to hospitals etc.

The expected results of the project:

- Reliable evidence data generated on Albanian public perceptions of corruption in the healthcare sector.

- Increased interaction and dialogue among key stakeholders on corruption issues affecting the healthcare sector.

- Enhanced understanding of health institutions' responses to corruption complaints addressed to them, identifying gaps and effective practices.;

- Boosted public awareness and engagement in reporting corrupt practices in the health sector;

- Increased media attention on corruption in the healthcare sector.

- At least 10,000 Albanian citizens reached through awareness-raising activities (online and in-person).

# PROJECT OBJECTIVE, PURPOSE & EXPECTED RESULTS

# 2.1 Overall objective

The overall objective of the project is to enhance transparency and accountability in the Albanian healthcare sector by fostering a culture of reporting of corrupt practices.

2.2 Specific objectives:

- To assess public perceptions and institutional response to corruption practices in health sector.

- To strengthen citizen engagement in actively reporting corruption in the health sector.

# SCOPE OF THE ASSIGNMENT

3.1 Objective of the assessment

In the framework of the project “Citizens for Transparency: Tackling Corruption in Albanian Healthcare sector” TFL is seeking to contract an expert / researcher to conduct an assessment of public perception of corruption in the healthcare sector.

The main goal of the assessment is to explore how the Albanian public views corruption in the healthcare sector, identify key areas of concern, understand the influencing factors, evaluate the level of trust the public has in healthcare institutions, assess public awareness of existing anti-corruption mechanisms, and propose potential solutions for improving the transparency and accountability in the healthcare sector.

# 3.2 Responsibilities of the expert/ researcher

The expert/ researcher will be responsible for overseeing and guiding the entire assessment preparation process, following the following steps:

- Conduct a literature review of existing legislation, studies and reports related to corruption in the Albanian healthcare sector to understand the context and define the framework for guiding the assessment preparation process. Prepare a summary report for the literature review, including a bibliography of the sources reviewed.

- Develop the assessment methodology and data collection instrument(s). Conduct a pilot test of the data collection instrument(s) to validate their effectiveness and make the required adjustments.

- Lead the data collection and analysis processes in adherence to ethical research practices. Identify key patterns, trends, and correlations in the public’s perceptions of corruption in the healthcare sector.

- Prepare of the assessment report. Submit the first draft of the assessment report, including the preliminary findings and recommendations for improving transparency and accountability in the Albanian healthcare sector.

- The final assessment report is submitted to the project staff and is accepted by the latter hen it is assessed that it                     is in line with the general objective formally and in terms of content.

- Present the findings of the assessment in a roundtable that will be organized with key national stakeholders.

- Ongoing communication with the TFL’s project team to provide updates on progress, address challenges, and ensure alignment with assessment objective.

3.3 Deliverables

The expert/ researcher will submit the following deliverables:

| Deliverables | Dateline |
| --- | --- |
| Assessment methodology and data collection instruments. (Detailed methodology for assessing public perceptions of corruption in Albanian healthcare sector, along with finalized data collection tools.) | 17 February 2025 |
| First draft of the Assessment Report (including preliminary findings and recommendations.) | 28 March 2025 |
| Final Assessment Report | 14 April 2025 |
| National Stakeholders roundtable presentation | TBC |

# ASSIGMENT MANAGEMENT

4.1 Responsible body

Together for Life

# TIMING OF THE ASIGNMENT

The assignment shall be completed by 14 April 2025. The maximum days of engagement of the expert will be up to 18 days starting from 29 January 2025.

# REQUIREMENTS FOR THE ASIGNMENT

  - Qualifications and selection criteria for the expert/ researcher

- Advanced degree in public health, social science, public policy or other related areas;

- Proven experience in conducting research related to healthcare systems, corruption, or governance.

- Experience in designing and implementing data collection instruments.

- Familiarity with anti-corruption frameworks and mechanisms, particularly in healthcare settings.

- Strong analytical and research skills, including qualitative and quantitative data analysis.

- Excellent writing and presentation skills.

- Ability to engage with diverse stakeholders and share complex findings.

# Proposal:

The expert is expected to submit the following documents:

- Curriculum Vitae.

- Tenders’ submission form (Annex A in the tender dossier)

- Technical proposal (Annex B in the tender dossier).

- Financial offer which indicates the fee per day for this duty (in Euro). (Annex C in the tender dossier).

# APPLICATION PROCESS

The deadline for submission of applications is 27 January 2025.

Applications must be submitted in English to the Contracting Authority in the email address info@togetherforlife.org.al or in the postal address:

# Together for Life

Rr. Brigada VIII, Pallati Jeshil Tekno-Projekt, Hyrja 2, Ap.14, Tiranë/ Shqipëri

## AWARD CRITERIA

The award criteria will be: Best value for money with the ratio of 80 points for technical offer and 20 points for financial offer.

| - Technical offer | 80 points |
| --- | --- |
| Organisation & Methodology | 40 |
| Work Experience | 40 |
| Educational Background | 20 |
| - Financial Offer | 20 points |
| TOTAL POINTS (A+B) | - POINTS |

## NOTIFICATION

Only short-listed candidates will be contacted for an interview.